## Start here
Mobilcab — 12-month organic marketing calendar
From docs/Mobilcab_12_Month_Organic_Marketing_Calendar.md · Week 1 = month -6 · launch = week 27
Settings
| Week 1 starts on (a Monday) | 2026-10-12 | Change this one date to move the whole plan, e.g. if the launch moves. Every date in the workbook follows it.
| Launch week | 27 | Fixed: the plan puts launch in week 27 (month -6 is weeks 1–4). Week labels L−26 … L+25 count from it.
| Launch date | 2027-04-12 | Calculated from the two cells above.
How to use it
| Weekly plan |  | The overview: one row per week, one column per platform, with a progress bar per week.
| Tasks |  | The checklist: one row per task. Pick ✓ in the Done column when it's done. Done rows turn green; tasks whose week has passed without a ✓ turn red. Use the filter arrows to see one week or one platform.
| Weekly numbers |  | Every Friday, fill in one row (the numbers come from Brevo, Plausible, Facebook and YouTube).
| Website steps |  | When to flip each switch in src/site.ts, and what it needs first.
| Deadlines |  | What has to be ready by which week. If one slips, move that week's announcement, not the trust-building around it.
| Content bank |  | Post ideas. Note the week you use one.
| Routine |  | The same short routine every week.
Legend
| Yellow cell, blue text |  | You fill this in (the start date, ✓ marks, notes, weekly numbers).
| Green row |  | Task done.
| Red row |  | Its week is over and it has no ✓ yet.
| [VERIFY] |  | A date or fact to confirm before relying on it (holidays, trade-show dates, app features).
| Time budget |  | If time runs short, cut the blog first, then social posting. Never cut Facebook group presence or customer support (Marketing Plan Section 11).

## Weekly plan
Weekly plan
Progress counts the ✓ marks on the Tasks sheet. Dates follow the start date on "Start here".
Week | Label | Week starts | Phase | Focus | Hours | Facebook groups | Facebook Page | YouTube | Blog | Email | Website | Other (offline, LinkedIn, beta, admin…) | Tasks | Done | Progress
1 | L−26 | 2026-10-12 | Month -6 · Quiet foundation | Set up the foundations | 10–12 h |  | • Create the Page: name, wordmark logo, cover, one-line description, link. No posts yet | • Create the channel (profile only, no videos yet) |  |  | • Deploy the coming-soon page (Git/GitHub, Vercel, domain, Brevo, Plausible: see README) | • Admin: Start SRL registration, Stripe account and e-Factura invoicing (Marketing Plan 4b) • Research: List 10–15 groups (search: tâmplari, mobilă la comandă, CNC lemn, proiectare mobilă) | 6 | 0 | 0%
2 | L−25 | 2026-10-19 | Month -6 · Quiet foundation | Join the groups | 10–12 h | • Join the 5–10 best groups; read each group's rules (links allowed? project mentions?) • Start the question log: every question carpenters ask, word for word | [5 empty] | • Legal: Send the Privacy Policy and Terms drafts to the lawyer (Privacy approval needed by week 12) | 4 | 0 | 0%
3 | L−24 | 2026-10-26 | Month -6 · Quiet foundation | Observe | 10–12 h | • Observe only: tone, recurring pain points, respected voices (anchor-customer candidates) | [5 empty] | • Content: Write 8–10 trade tips for the content bank | 3 | 0 | 0%
4 | L−23 | 2026-11-02 | Month -6 · Quiet foundation | Plan the offline side | 10–12 h | [6 empty] | • Research: Find APMR and regional wood-cluster contacts • Research: Look up 2027 dates for BIFE-SIM and regional fairs [VERIFY] • Review: Monthly review: confirmed sign-ups, confirmation rate | 4 | 0 | 0%
5 | L−22 | 2026-11-09 | Month -5 · Trust-building | Start helping | 10–12 h | • Answer 3–5 real questions properly, no self-promotion; update the question log | • First post: trade tip ("Cum calculezi lățimea polițelor între laterale") |  |  |  |  | • Anchor customer: Keep talking with the 2–3 candidates as a peer, no pitch | 4 | 0 | 0%
6 | L−21 | 2026-11-16 | Month -5 · Trust-building | First video, first association contact | 10–12 h | • Answer 3–5 real questions properly, no self-promotion; update the question log |  | • First short video (2–4 min): a generic trade tip, not about the app |  |  |  | • Associations: Introductory email to APMR (learning, not pitching) • Anchor customer: Keep talking with the 2–3 candidates as a peer, no pitch | 5 | 0 | 0%
7 | L−20 | 2026-11-23 | Month -5 · Trust-building | Validate price and free plan | 10–12 h | • Answer 3–5 real questions properly, no self-promotion; update the question log | • Trade tip #2 |  |  |  |  | • Validation: Ask 5–10 people privately what would make them try a new tool, what they use, a fair monthly price (Marketing Plan 3b) • Anchor customer: Keep talking with the 2–3 candidates as a peer, no pitch | 5 | 0 | 0%
8 | L−19 | 2026-11-30 | Month -5 · Trust-building | Workshop visits (1 Dec: National Day) | 10–12 h | • Answer 3–5 real questions properly, no self-promotion; update the question log | [5 empty] | • Offline: Visit 2–3 local workshops (with permission) and watch how they design and cut • Anchor customer: Keep talking with the 2–3 candidates as a peer, no pitch • Review: Monthly review | 5 | 0 | 0%
9 | L−18 | 2026-12-07 | Month -4 · Soft mentions + referrals | First soft mentions | 8–12 h | • Keep answering; where relevant and allowed, mention "lucrez chiar la ceva pentru problema asta" in a comment (no link unless asked) | • First behind-the-scenes post: a WIP screenshot | [5 empty] | 3 | 0 | 0%
10 | L−17 | 2026-12-14 | Month -4 · Soft mentions + referrals | First build log | 8–12 h | • Keep answering questions (never stop this) | • Behind the scenes: WIP #2 |  |  | • First monthly build log ("jurnal de construcție") to the confirmed waitlist: 150–250 words + a screenshot |  |  | 4 | 0 | 0%
11 | L−16 | 2026-12-21 | Month -4 · Soft mentions + referrals | Holidays (Christmas): no announcements | 8–12 h | • Replies only | • One light seasonal post |  |  |  |  | • Prep: Lawyer approval of the Privacy Policy; fill in EMAIL_SETTINGS; rebuild the emails | 4 | 0 | 0%
12 | L−15 | 2026-12-28 | Month -4 · Soft mentions + referrals | Holidays (New Year): no announcements | 8–12 h | • Replies only | [5 empty] | • Prep: Get week 13 ready: npm run test:all, check-launch, draft the invite-program posts | 3 | 0 | 0%
13 | L−14 | 2027-01-04 | Month -4 · Soft mentions + referrals | REFERRAL LAUNCH | 8–12 h | • At most one own value-led post per group this month, only where allowed | • Announce the invite program; pin it |  |  | • New-year update + invite program: 3 confirmed invites = a guaranteed private-beta place | • Publish Home + Privacy; REFERRAL_PROGRAM = true; rebuild + re-paste the emails; deploy | • WhatsApp: Share your own invite link with carpenters you know personally | 6 | 0 | 0%
14 | L−13 | 2027-01-11 | Month -3 · Private beta | Choose the beta testers | 12–14 h | • Keep answering questions (never stop this) |  |  |  | • Build log #2: the private beta has started |  | • Beta: Pick 15–20 testers (everyone with 3+ confirmed invites, the anchor customer, the warmest contacts); invite each personally | 4 | 0 | 0%
15 | L−12 | 2027-01-18 | Month -3 · Private beta | Private beta: onboarding | 12–14 h | • Keep answering questions (never stop this) | • Behind the scenes: what we learned in the beta (with permission) |  |  |  |  | • Beta: 5–7 one-to-one onboarding sessions (~45 min); ask permission to record and to quote | 4 | 0 | 0%
16 | L−11 | 2027-01-25 | Month -3 · Private beta | FOUNDING PARTNER RESERVATIONS OPEN | 12–14 h | • Keep answering questions (never stop this) | • Founding Partner program post (co-creation framing) |  |  | • 100 Founding Partner spots: reserve now, nothing to pay | • Publish the Founding Partner page (set BREVO_FP_LIST_ID first) | • Beta: 5–7 one-to-one onboarding sessions (~45 min); ask permission to record and to quote | 6 | 0 | 0%
17 | L−10 | 2027-02-01 | Month -3 · Private beta | Private beta: onboarding | 12–14 h | • Keep answering questions (never stop this) | • Behind the scenes: beta update |  |  |  |  | • Beta: 5–7 one-to-one onboarding sessions (~45 min); ask permission to record and to quote • Review: Monthly review: reservations, beta activation (first export), feedback themes | 5 | 0 | 0%
18 | L−9 | 2027-02-08 | Month -2 · Proof building | Demo 1 + blog post 1 | 12 h | • Link the blog post in a comment where a question matches |  | • Record demo 1 (design flow) on a real beta project (Launch Content Kit 2.1) | • Publish post 1 "Program proiectare mobilă gratuit…" after verifying competitor facts (blog: true) | • Build log #3 |  |  | 5 | 0 | 0%
19 | L−8 | 2027-02-15 | Month -2 · Proof building | Demo 2 + blog post 2 | 12 h | • Keep answering questions (never stop this) |  | • Record demo 2 (AI assistant, Kit 2.2) | • Publish post 2 "Cum faci cutlist pentru CNC…" |  |  |  | 4 | 0 | 0%
20 | L−7 | 2027-02-22 | Month -2 · Proof building | Demo 3 + blog post 3 + Demo page | 12 h | • Keep answering questions (never stop this) |  | • Record demo 3 (cutlist/CNC export, Kit 2.3); upload all three | • Publish post 3 "Polyboard vs. alternative cloud-based" |  | • Publish the Demo page; add the video IDs to src/data/demoVideos.ts |  | 5 | 0 | 0%
21 | L−6 | 2027-03-01 | Month -2 · Proof building | Social proof | 12 h | • First demo-clip post in 1–2 groups where you're well known | • Testimonial post #1 (tag the tester if they agree) |  |  |  | • Publish the FAQ; add 3–5 real testimonials to src/data/testimonials.ts |  | 4 | 0 | 0%
22 | L−5 | 2027-03-08 | Month -2 · Proof building | Final decisions | 12 h | • Keep answering questions (never stop this) | [5 empty] | • Decide: Final prices, free-plan limits, Founding Partner terms (open questions in DECISIONS.md) • Review: Monthly review | 4 | 0 | 0%
23 | L−4 | 2027-03-15 | Month -1 · Countdown | Countdown: 4 weeks | 12–14 h | • Keep answering questions (never stop this) | • Countdown #1 ("4 săptămâni") |  |  | • Launch date announced: "Pe 12 aprilie lansăm" | • Publish Pricing + Terms (lawyer-approved) | • Anchor customer: Agree how they'll take part at launch • Development: Stripe payments working (make a test payment) | 7 | 0 | 0%
24 | L−3 | 2027-03-22 | Month -1 · Countdown | Countdown: 3 weeks | 12–14 h | • Value post with the launch date at the end, where allowed | • Countdown #2: a short demo clip | • Tutorial #2 (from the question log) |  |  |  |  | 4 | 0 | 0%
25 | L−2 | 2027-03-29 | Month -1 · Countdown | Countdown: 2 weeks | 12–14 h | • Keep answering questions (never stop this) | • Countdown #3: a testimonial |  |  |  |  | • Launch prep: Finalise the founder-story post for each group (Launch Content Kit 3.1) • Support: Answers ready for the 5–10 most likely questions | 5 | 0 | 0%
26 | L−1 | 2027-04-05 | Month -1 · Countdown | Countdown: next week | 12–14 h | • Keep answering questions (never stop this) | • Countdown #4 ("săptămâna viitoare") |  |  | • Launching next week + Founding Partner spots left | • Final checks: npm run test:all, check-launch, a test payment, every Brevo email |  | 5 | 0 | 0%
27 | L+0 | 2027-04-12 | Launch month | LAUNCH | ~20 h | • Founder-story post in each group, spread over the day, adapted per group (link in the comments) | • Founder-story post, pinned |  |  | • To the whole waitlist: "Mobilcab e live — locurile Founding Partner sunt deschise" | • Day 1: productPublic = true; deploy; Founding Partner payments live | • Anchor customer: Comments and shares • Support: Reply to every comment and message the same day | 7 | 0 | 0%
28 | L+1 | 2027-04-19 | Launch month | Launch follow-up | ~20 h | • Replies only | • First real user project (with permission) | • "Răspund la întrebările voastre" video from launch-week questions |  |  |  | • Onboarding: Concierge sessions for new Founding Partners | 5 | 0 | 0%
29 | L+2 | 2027-04-26 | Launch month | Transparency | ~20 h | • Replies only; don't re-post the launch | • "What we fixed in week 1" post | [5 empty] | 3 | 0 | 0%
30 | L+3 | 2027-05-03 | Launch month | Light week (1 May; Orthodox Easter 2 May [VERIFY]) | ~20 h |  | • One post |  |  |  |  | • Review: Launch-month review: sign-ups, Founding Partners, activation, top questions | 3 | 0 | 0%
31 | L+4 | 2027-05-10 | Phase 1 · Romania growth | First changelog | 8–10 h | • Answer questions (about 2 h) | • 2 posts this week | • Tutorial #3 | • Post 4, from the most common question in the log | • First monthly changelog to paying users (Marketing Plan 6a) |  |  | 6 | 0 | 0%
32 | L+5 | 2027-05-17 | Phase 1 · Romania growth | Case study #1 | 8–10 h | • Answer questions (about 2 h) | • 2 posts this week |  |  |  |  | • Case study: Case study #1 with the anchor customer (project, time saved) | 4 | 0 | 0%
33 | L+6 | 2027-05-24 | Phase 1 · Romania growth | Publish case study #1 | 8–10 h | • Share case study #1 where relevant; answer questions | • Publish case study #1 (+1 more post) | [5 empty] | 3 | 0 | 0%
34 | L+7 | 2027-05-31 | Phase 1 · Romania growth | Offline | 8–10 h | • Answer questions (about 2 h) | • 2 posts this week |  |  |  |  | • Offline: A regional fair, or 3 workshop visits with a tablet demo | 4 | 0 | 0%
35 | L+8 | 2027-06-07 | Phase 1 · Romania growth | Newsletter | 8–10 h | • Answer questions (about 2 h) | • 2 posts this week | • Tutorial #4 |  | • Monthly newsletter to free users and the waitlist |  |  | 5 | 0 | 0%
36 | L+9 | 2027-06-14 | Phase 1 · Romania growth | Retention | 8–10 h | • Answer questions (about 2 h) | • 2 posts this week |  |  |  |  | • Retention: Personal "need help?" message to paying users inactive for 14+ days (6a) | 4 | 0 | 0%
37 | L+10 | 2027-06-21 | Phase 1 · Romania growth | Blog + testimonial (Rusalii 20–21 June [VERIFY]) | 8–10 h | • Answer questions (about 2 h) | • Testimonial #2 (+1 more post) |  | • Post 5 |  |  |  | 4 | 0 | 0%
38 | L+11 | 2027-06-28 | Phase 1 · Romania growth | Founding Partner check-ins | 8–10 h | • Answer questions (about 2 h) | • 2 posts this week |  |  |  |  | • Retention: Quarterly check-in with every Founding Partner (6a) | 4 | 0 | 0%
39 | L+12 | 2027-07-05 | Phase 1 · Romania growth | Phase 1 review | 8–10 h | • Answer questions (about 2 h) | • 2 posts this week |  |  |  |  | • Review: Phase 1 review vs goal: 100–300 users, 10–30 paying Founding Partners, 2–3 case studies | 4 | 0 | 0%
40 | L+13 | 2027-07-12 | Phase 2 · New segments | Start Phase 2: LinkedIn + designers | 8–10 h | • Answer questions (about 2 h) | • 2 posts this week |  |  |  |  | • LinkedIn: Company page + refreshed founder profile • Groups: Join designer/architect groups (Facebook + LinkedIn); observe 2–3 weeks | 5 | 0 | 0%
41 | L+14 | 2027-07-19 | Phase 2 · New segments | Case study #2 | 8–10 h | • Answer questions (about 2 h) | • 2 posts this week |  |  |  |  | • Case study: Case study #2 • Designers: Client-presentation angle, only if the app really shares live designs [VERIFY] | 5 | 0 | 0%
42 | L+15 | 2027-07-26 | Phase 2 · New segments | Design schools | 8–10 h | • Answer questions (about 2 h) | • 2 posts this week |  |  |  |  | • Partnerships: Contact 1–2 design schools about an autumn webinar | 4 | 0 | 0%
43 | L+16 | 2027-08-02 | Phase 2 · New segments | August: lighter cadence | 8–10 h | • Answer questions (about 2 h) | • 1 post | • 1 video |  |  |  | • Prep: Webinar content + a partnership one-pager (users, case studies) | 5 | 0 | 0%
44 | L+17 | 2027-08-09 | Phase 2 · New segments | Partnerships | 8–10 h | • Answer questions (about 2 h) | • 1 post | • 1 video |  |  |  | • Partnerships: Write to fittings distributors (Blum, Hettich, GTV) and CNC sellers in Romania | 5 | 0 | 0%
45 | L+18 | 2027-08-16 | Phase 2 · New segments | August: lighter cadence | 8–10 h | • Answer questions (about 2 h) | • 1 post | • 1 video |  |  |  | • Prep: Follow up on partnership replies | 5 | 0 | 0%
46 | L+19 | 2027-08-23 | Phase 2 · New segments | August: lighter cadence (15 Aug holiday) | 8–10 h | • Answer questions (about 2 h) | • 1 post | • 1 video |  |  |  |  | 4 | 0 | 0%
47 | L+20 | 2027-08-30 | Phase 2 · New segments | Manufacturers | 8–10 h | • Answer questions (about 2 h) | • 2 posts this week |  |  |  |  | • LinkedIn: 5 direct conversations with manufacturers, using the case studies | 4 | 0 | 0%
48 | L+21 | 2027-09-06 | Phase 2 · New segments | Webinar | 8–10 h | • Answer questions (about 2 h) | • 2 posts this week |  |  |  |  | • Webinar: Design-school webinar, or a Facebook Live demo | 4 | 0 | 0%
49 | L+22 | 2027-09-13 | Phase 2 · New segments | Content for designers | 8–10 h | • Answer questions (about 2 h) | • 2 posts this week | • A video for designers | • A post for designers |  |  |  | 5 | 0 | 0%
50 | L+23 | 2027-09-20 | Phase 2 · New segments | Trade show | 8–10 h | • Answer questions (about 2 h) | • 2 posts this week |  |  |  |  | • Trade show: BIFE-SIM or a regional fair if the dates fall here: tablet demos, 20–30 conversations | 4 | 0 | 0%
51 | L+24 | 2027-09-27 | Phase 2 · New segments | Retention set-up | 8–10 h | • Answer questions (about 2 h) | • 2 posts this week |  |  |  |  | • Retention: Win-back email for cancelled users; plan Founding Partner renewal reminders (April 2028) | 4 | 0 | 0%
52 | L+25 | 2027-10-04 | Phase 2 · New segments | Year review | 8–10 h | • Answer questions (about 2 h) | • 2 posts this week |  |  |  |  | • Review: Year review: best channels for confirmed sign-ups and paying users; plan year 2 | 4 | 0 | 0%
Formulas:
Week starts = 'Start here'!$C6+7*([Week]-1)

## Tasks
Tasks
Pick ✓ in "Done" when a task is finished. Filter by week or platform with the arrows in row 4.
Week | Week starts | Phase | Platform | Task | Done | Notes
1 | 2026-10-12 | Month -6 · Quiet foundation | Facebook Page | Create the Page: name, wordmark logo, cover, one-line description, link. No posts yet
1 | 2026-10-12 | Month -6 · Quiet foundation | YouTube | Create the channel (profile only, no videos yet)
1 | 2026-10-12 | Month -6 · Quiet foundation | Website | Deploy the coming-soon page (Git/GitHub, Vercel, domain, Brevo, Plausible: see README)
1 | 2026-10-12 | Month -6 · Quiet foundation | Admin | Start SRL registration, Stripe account and e-Factura invoicing (Marketing Plan 4b)
1 | 2026-10-12 | Month -6 · Quiet foundation | Research | List 10–15 groups (search: tâmplari, mobilă la comandă, CNC lemn, proiectare mobilă)
1 | 2026-10-12 | Month -6 · Quiet foundation | Routine | Weekly routine + Friday numbers (see Routine and Weekly numbers)
2 | 2026-10-19 | Month -6 · Quiet foundation | Facebook groups | Join the 5–10 best groups; read each group's rules (links allowed? project mentions?)
2 | 2026-10-19 | Month -6 · Quiet foundation | Facebook groups | Start the question log: every question carpenters ask, word for word
2 | 2026-10-19 | Month -6 · Quiet foundation | Legal | Send the Privacy Policy and Terms drafts to the lawyer (Privacy approval needed by week 12)
2 | 2026-10-19 | Month -6 · Quiet foundation | Routine | Weekly routine + Friday numbers (see Routine and Weekly numbers)
3 | 2026-10-26 | Month -6 · Quiet foundation | Facebook groups | Observe only: tone, recurring pain points, respected voices (anchor-customer candidates)
3 | 2026-10-26 | Month -6 · Quiet foundation | Content | Write 8–10 trade tips for the content bank
3 | 2026-10-26 | Month -6 · Quiet foundation | Routine | Weekly routine + Friday numbers (see Routine and Weekly numbers)
4 | 2026-11-02 | Month -6 · Quiet foundation | Research | Find APMR and regional wood-cluster contacts
4 | 2026-11-02 | Month -6 · Quiet foundation | Research | Look up 2027 dates for BIFE-SIM and regional fairs [VERIFY]
4 | 2026-11-02 | Month -6 · Quiet foundation | Review | Monthly review: confirmed sign-ups, confirmation rate
4 | 2026-11-02 | Month -6 · Quiet foundation | Routine | Weekly routine + Friday numbers (see Routine and Weekly numbers)
5 | 2026-11-09 | Month -5 · Trust-building | Facebook groups | Answer 3–5 real questions properly, no self-promotion; update the question log
5 | 2026-11-09 | Month -5 · Trust-building | Facebook Page | First post: trade tip ("Cum calculezi lățimea polițelor între laterale")
5 | 2026-11-09 | Month -5 · Trust-building | Anchor customer | Keep talking with the 2–3 candidates as a peer, no pitch
5 | 2026-11-09 | Month -5 · Trust-building | Routine | Weekly routine + Friday numbers (see Routine and Weekly numbers)
6 | 2026-11-16 | Month -5 · Trust-building | Facebook groups | Answer 3–5 real questions properly, no self-promotion; update the question log
6 | 2026-11-16 | Month -5 · Trust-building | YouTube | First short video (2–4 min): a generic trade tip, not about the app
6 | 2026-11-16 | Month -5 · Trust-building | Associations | Introductory email to APMR (learning, not pitching)
6 | 2026-11-16 | Month -5 · Trust-building | Anchor customer | Keep talking with the 2–3 candidates as a peer, no pitch
6 | 2026-11-16 | Month -5 · Trust-building | Routine | Weekly routine + Friday numbers (see Routine and Weekly numbers)
7 | 2026-11-23 | Month -5 · Trust-building | Facebook groups | Answer 3–5 real questions properly, no self-promotion; update the question log
7 | 2026-11-23 | Month -5 · Trust-building | Facebook Page | Trade tip #2
7 | 2026-11-23 | Month -5 · Trust-building | Validation | Ask 5–10 people privately what would make them try a new tool, what they use, a fair monthly price (Marketing Plan 3b)
7 | 2026-11-23 | Month -5 · Trust-building | Anchor customer | Keep talking with the 2–3 candidates as a peer, no pitch
7 | 2026-11-23 | Month -5 · Trust-building | Routine | Weekly routine + Friday numbers (see Routine and Weekly numbers)
8 | 2026-11-30 | Month -5 · Trust-building | Facebook groups | Answer 3–5 real questions properly, no self-promotion; update the question log
8 | 2026-11-30 | Month -5 · Trust-building | Offline | Visit 2–3 local workshops (with permission) and watch how they design and cut
8 | 2026-11-30 | Month -5 · Trust-building | Anchor customer | Keep talking with the 2–3 candidates as a peer, no pitch
8 | 2026-11-30 | Month -5 · Trust-building | Review | Monthly review
8 | 2026-11-30 | Month -5 · Trust-building | Routine | Weekly routine + Friday numbers (see Routine and Weekly numbers)
9 | 2026-12-07 | Month -4 · Soft mentions + referrals | Facebook groups | Keep answering; where relevant and allowed, mention "lucrez chiar la ceva pentru problema asta" in a comment (no link unless asked)
9 | 2026-12-07 | Month -4 · Soft mentions + referrals | Facebook Page | First behind-the-scenes post: a WIP screenshot
9 | 2026-12-07 | Month -4 · Soft mentions + referrals | Routine | Weekly routine + Friday numbers (see Routine and Weekly numbers)
10 | 2026-12-14 | Month -4 · Soft mentions + referrals | Facebook groups | Keep answering questions (never stop this)
10 | 2026-12-14 | Month -4 · Soft mentions + referrals | Facebook Page | Behind the scenes: WIP #2
10 | 2026-12-14 | Month -4 · Soft mentions + referrals | Email | First monthly build log ("jurnal de construcție") to the confirmed waitlist: 150–250 words + a screenshot
10 | 2026-12-14 | Month -4 · Soft mentions + referrals | Routine | Weekly routine + Friday numbers (see Routine and Weekly numbers)
11 | 2026-12-21 | Month -4 · Soft mentions + referrals | Facebook groups | Replies only
11 | 2026-12-21 | Month -4 · Soft mentions + referrals | Facebook Page | One light seasonal post
11 | 2026-12-21 | Month -4 · Soft mentions + referrals | Prep | Lawyer approval of the Privacy Policy; fill in EMAIL_SETTINGS; rebuild the emails
11 | 2026-12-21 | Month -4 · Soft mentions + referrals | Routine | Weekly routine + Friday numbers (see Routine and Weekly numbers)
12 | 2026-12-28 | Month -4 · Soft mentions + referrals | Facebook groups | Replies only
12 | 2026-12-28 | Month -4 · Soft mentions + referrals | Prep | Get week 13 ready: npm run test:all, check-launch, draft the invite-program posts
12 | 2026-12-28 | Month -4 · Soft mentions + referrals | Routine | Weekly routine + Friday numbers (see Routine and Weekly numbers)
13 | 2027-01-04 | Month -4 · Soft mentions + referrals | Facebook groups | At most one own value-led post per group this month, only where allowed
13 | 2027-01-04 | Month -4 · Soft mentions + referrals | Facebook Page | Announce the invite program; pin it
13 | 2027-01-04 | Month -4 · Soft mentions + referrals | Email | New-year update + invite program: 3 confirmed invites = a guaranteed private-beta place
13 | 2027-01-04 | Month -4 · Soft mentions + referrals | Website | Publish Home + Privacy; REFERRAL_PROGRAM = true; rebuild + re-paste the emails; deploy
13 | 2027-01-04 | Month -4 · Soft mentions + referrals | WhatsApp | Share your own invite link with carpenters you know personally
13 | 2027-01-04 | Month -4 · Soft mentions + referrals | Routine | Weekly routine + Friday numbers (see Routine and Weekly numbers)
14 | 2027-01-11 | Month -3 · Private beta | Facebook groups | Keep answering questions (never stop this)
14 | 2027-01-11 | Month -3 · Private beta | Email | Build log #2: the private beta has started
14 | 2027-01-11 | Month -3 · Private beta | Beta | Pick 15–20 testers (everyone with 3+ confirmed invites, the anchor customer, the warmest contacts); invite each personally
14 | 2027-01-11 | Month -3 · Private beta | Routine | Weekly routine + Friday numbers (see Routine and Weekly numbers)
15 | 2027-01-18 | Month -3 · Private beta | Facebook groups | Keep answering questions (never stop this)
15 | 2027-01-18 | Month -3 · Private beta | Facebook Page | Behind the scenes: what we learned in the beta (with permission)
15 | 2027-01-18 | Month -3 · Private beta | Beta | 5–7 one-to-one onboarding sessions (~45 min); ask permission to record and to quote
15 | 2027-01-18 | Month -3 · Private beta | Routine | Weekly routine + Friday numbers (see Routine and Weekly numbers)
16 | 2027-01-25 | Month -3 · Private beta | Facebook groups | Keep answering questions (never stop this)
16 | 2027-01-25 | Month -3 · Private beta | Facebook Page | Founding Partner program post (co-creation framing)
16 | 2027-01-25 | Month -3 · Private beta | Email | 100 Founding Partner spots: reserve now, nothing to pay
16 | 2027-01-25 | Month -3 · Private beta | Website | Publish the Founding Partner page (set BREVO_FP_LIST_ID first)
16 | 2027-01-25 | Month -3 · Private beta | Beta | 5–7 one-to-one onboarding sessions (~45 min); ask permission to record and to quote
16 | 2027-01-25 | Month -3 · Private beta | Routine | Weekly routine + Friday numbers (see Routine and Weekly numbers)
17 | 2027-02-01 | Month -3 · Private beta | Facebook groups | Keep answering questions (never stop this)
17 | 2027-02-01 | Month -3 · Private beta | Facebook Page | Behind the scenes: beta update
17 | 2027-02-01 | Month -3 · Private beta | Beta | 5–7 one-to-one onboarding sessions (~45 min); ask permission to record and to quote
17 | 2027-02-01 | Month -3 · Private beta | Review | Monthly review: reservations, beta activation (first export), feedback themes
17 | 2027-02-01 | Month -3 · Private beta | Routine | Weekly routine + Friday numbers (see Routine and Weekly numbers)
18 | 2027-02-08 | Month -2 · Proof building | Facebook groups | Link the blog post in a comment where a question matches
18 | 2027-02-08 | Month -2 · Proof building | YouTube | Record demo 1 (design flow) on a real beta project (Launch Content Kit 2.1)
18 | 2027-02-08 | Month -2 · Proof building | Blog | Publish post 1 "Program proiectare mobilă gratuit…" after verifying competitor facts (blog: true)
18 | 2027-02-08 | Month -2 · Proof building | Email | Build log #3
18 | 2027-02-08 | Month -2 · Proof building | Routine | Weekly routine + Friday numbers (see Routine and Weekly numbers)
19 | 2027-02-15 | Month -2 · Proof building | Facebook groups | Keep answering questions (never stop this)
19 | 2027-02-15 | Month -2 · Proof building | YouTube | Record demo 2 (AI assistant, Kit 2.2)
19 | 2027-02-15 | Month -2 · Proof building | Blog | Publish post 2 "Cum faci cutlist pentru CNC…"
19 | 2027-02-15 | Month -2 · Proof building | Routine | Weekly routine + Friday numbers (see Routine and Weekly numbers)
20 | 2027-02-22 | Month -2 · Proof building | Facebook groups | Keep answering questions (never stop this)
20 | 2027-02-22 | Month -2 · Proof building | YouTube | Record demo 3 (cutlist/CNC export, Kit 2.3); upload all three
20 | 2027-02-22 | Month -2 · Proof building | Blog | Publish post 3 "Polyboard vs. alternative cloud-based"
20 | 2027-02-22 | Month -2 · Proof building | Website | Publish the Demo page; add the video IDs to src/data/demoVideos.ts
20 | 2027-02-22 | Month -2 · Proof building | Routine | Weekly routine + Friday numbers (see Routine and Weekly numbers)
21 | 2027-03-01 | Month -2 · Proof building | Facebook groups | First demo-clip post in 1–2 groups where you're well known
21 | 2027-03-01 | Month -2 · Proof building | Facebook Page | Testimonial post #1 (tag the tester if they agree)
21 | 2027-03-01 | Month -2 · Proof building | Website | Publish the FAQ; add 3–5 real testimonials to src/data/testimonials.ts
21 | 2027-03-01 | Month -2 · Proof building | Routine | Weekly routine + Friday numbers (see Routine and Weekly numbers)
22 | 2027-03-08 | Month -2 · Proof building | Facebook groups | Keep answering questions (never stop this)
22 | 2027-03-08 | Month -2 · Proof building | Decide | Final prices, free-plan limits, Founding Partner terms (open questions in DECISIONS.md)
22 | 2027-03-08 | Month -2 · Proof building | Review | Monthly review
22 | 2027-03-08 | Month -2 · Proof building | Routine | Weekly routine + Friday numbers (see Routine and Weekly numbers)
23 | 2027-03-15 | Month -1 · Countdown | Facebook groups | Keep answering questions (never stop this)
23 | 2027-03-15 | Month -1 · Countdown | Facebook Page | Countdown #1 ("4 săptămâni")
23 | 2027-03-15 | Month -1 · Countdown | Email | Launch date announced: "Pe 12 aprilie lansăm"
23 | 2027-03-15 | Month -1 · Countdown | Website | Publish Pricing + Terms (lawyer-approved)
23 | 2027-03-15 | Month -1 · Countdown | Anchor customer | Agree how they'll take part at launch
23 | 2027-03-15 | Month -1 · Countdown | Development | Stripe payments working (make a test payment)
23 | 2027-03-15 | Month -1 · Countdown | Routine | Weekly routine + Friday numbers (see Routine and Weekly numbers)
24 | 2027-03-22 | Month -1 · Countdown | Facebook groups | Value post with the launch date at the end, where allowed
24 | 2027-03-22 | Month -1 · Countdown | Facebook Page | Countdown #2: a short demo clip
24 | 2027-03-22 | Month -1 · Countdown | YouTube | Tutorial #2 (from the question log)
24 | 2027-03-22 | Month -1 · Countdown | Routine | Weekly routine + Friday numbers (see Routine and Weekly numbers)
25 | 2027-03-29 | Month -1 · Countdown | Facebook groups | Keep answering questions (never stop this)
25 | 2027-03-29 | Month -1 · Countdown | Facebook Page | Countdown #3: a testimonial
25 | 2027-03-29 | Month -1 · Countdown | Launch prep | Finalise the founder-story post for each group (Launch Content Kit 3.1)
25 | 2027-03-29 | Month -1 · Countdown | Support | Answers ready for the 5–10 most likely questions
25 | 2027-03-29 | Month -1 · Countdown | Routine | Weekly routine + Friday numbers (see Routine and Weekly numbers)
26 | 2027-04-05 | Month -1 · Countdown | Facebook groups | Keep answering questions (never stop this)
26 | 2027-04-05 | Month -1 · Countdown | Facebook Page | Countdown #4 ("săptămâna viitoare")
26 | 2027-04-05 | Month -1 · Countdown | Email | Launching next week + Founding Partner spots left
26 | 2027-04-05 | Month -1 · Countdown | Website | Final checks: npm run test:all, check-launch, a test payment, every Brevo email
26 | 2027-04-05 | Month -1 · Countdown | Routine | Weekly routine + Friday numbers (see Routine and Weekly numbers)
27 | 2027-04-12 | Launch month | Facebook groups | Founder-story post in each group, spread over the day, adapted per group (link in the comments)
27 | 2027-04-12 | Launch month | Facebook Page | Founder-story post, pinned
27 | 2027-04-12 | Launch month | Email | To the whole waitlist: "Mobilcab e live — locurile Founding Partner sunt deschise"
27 | 2027-04-12 | Launch month | Website | Day 1: productPublic = true; deploy; Founding Partner payments live
27 | 2027-04-12 | Launch month | Anchor customer | Comments and shares
27 | 2027-04-12 | Launch month | Support | Reply to every comment and message the same day
27 | 2027-04-12 | Launch month | Routine | Weekly routine + Friday numbers (see Routine and Weekly numbers)
28 | 2027-04-19 | Launch month | Facebook groups | Replies only
28 | 2027-04-19 | Launch month | Facebook Page | First real user project (with permission)
28 | 2027-04-19 | Launch month | YouTube | "Răspund la întrebările voastre" video from launch-week questions
28 | 2027-04-19 | Launch month | Onboarding | Concierge sessions for new Founding Partners
28 | 2027-04-19 | Launch month | Routine | Weekly routine + Friday numbers (see Routine and Weekly numbers)
29 | 2027-04-26 | Launch month | Facebook groups | Replies only; don't re-post the launch
29 | 2027-04-26 | Launch month | Facebook Page | "What we fixed in week 1" post
29 | 2027-04-26 | Launch month | Routine | Weekly routine + Friday numbers (see Routine and Weekly numbers)
30 | 2027-05-03 | Launch month | Facebook Page | One post
30 | 2027-05-03 | Launch month | Review | Launch-month review: sign-ups, Founding Partners, activation, top questions
30 | 2027-05-03 | Launch month | Routine | Weekly routine + Friday numbers (see Routine and Weekly numbers)
31 | 2027-05-10 | Phase 1 · Romania growth | Facebook groups | Answer questions (about 2 h)
31 | 2027-05-10 | Phase 1 · Romania growth | Facebook Page | 2 posts this week
31 | 2027-05-10 | Phase 1 · Romania growth | YouTube | Tutorial #3
31 | 2027-05-10 | Phase 1 · Romania growth | Blog | Post 4, from the most common question in the log
31 | 2027-05-10 | Phase 1 · Romania growth | Email | First monthly changelog to paying users (Marketing Plan 6a)
31 | 2027-05-10 | Phase 1 · Romania growth | Routine | Weekly routine + Friday numbers (see Routine and Weekly numbers)
32 | 2027-05-17 | Phase 1 · Romania growth | Facebook groups | Answer questions (about 2 h)
32 | 2027-05-17 | Phase 1 · Romania growth | Facebook Page | 2 posts this week
32 | 2027-05-17 | Phase 1 · Romania growth | Case study | Case study #1 with the anchor customer (project, time saved)
32 | 2027-05-17 | Phase 1 · Romania growth | Routine | Weekly routine + Friday numbers (see Routine and Weekly numbers)
33 | 2027-05-24 | Phase 1 · Romania growth | Facebook groups | Share case study #1 where relevant; answer questions
33 | 2027-05-24 | Phase 1 · Romania growth | Facebook Page | Publish case study #1 (+1 more post)
33 | 2027-05-24 | Phase 1 · Romania growth | Routine | Weekly routine + Friday numbers (see Routine and Weekly numbers)
34 | 2027-05-31 | Phase 1 · Romania growth | Facebook groups | Answer questions (about 2 h)
34 | 2027-05-31 | Phase 1 · Romania growth | Facebook Page | 2 posts this week
34 | 2027-05-31 | Phase 1 · Romania growth | Offline | A regional fair, or 3 workshop visits with a tablet demo
34 | 2027-05-31 | Phase 1 · Romania growth | Routine | Weekly routine + Friday numbers (see Routine and Weekly numbers)
35 | 2027-06-07 | Phase 1 · Romania growth | Facebook groups | Answer questions (about 2 h)
35 | 2027-06-07 | Phase 1 · Romania growth | Facebook Page | 2 posts this week
35 | 2027-06-07 | Phase 1 · Romania growth | YouTube | Tutorial #4
35 | 2027-06-07 | Phase 1 · Romania growth | Email | Monthly newsletter to free users and the waitlist
35 | 2027-06-07 | Phase 1 · Romania growth | Routine | Weekly routine + Friday numbers (see Routine and Weekly numbers)
36 | 2027-06-14 | Phase 1 · Romania growth | Facebook groups | Answer questions (about 2 h)
36 | 2027-06-14 | Phase 1 · Romania growth | Facebook Page | 2 posts this week
36 | 2027-06-14 | Phase 1 · Romania growth | Retention | Personal "need help?" message to paying users inactive for 14+ days (6a)
36 | 2027-06-14 | Phase 1 · Romania growth | Routine | Weekly routine + Friday numbers (see Routine and Weekly numbers)
37 | 2027-06-21 | Phase 1 · Romania growth | Facebook groups | Answer questions (about 2 h)
37 | 2027-06-21 | Phase 1 · Romania growth | Facebook Page | Testimonial #2 (+1 more post)
37 | 2027-06-21 | Phase 1 · Romania growth | Blog | Post 5
37 | 2027-06-21 | Phase 1 · Romania growth | Routine | Weekly routine + Friday numbers (see Routine and Weekly numbers)
38 | 2027-06-28 | Phase 1 · Romania growth | Facebook groups | Answer questions (about 2 h)
38 | 2027-06-28 | Phase 1 · Romania growth | Facebook Page | 2 posts this week
38 | 2027-06-28 | Phase 1 · Romania growth | Retention | Quarterly check-in with every Founding Partner (6a)
38 | 2027-06-28 | Phase 1 · Romania growth | Routine | Weekly routine + Friday numbers (see Routine and Weekly numbers)
39 | 2027-07-05 | Phase 1 · Romania growth | Facebook groups | Answer questions (about 2 h)
39 | 2027-07-05 | Phase 1 · Romania growth | Facebook Page | 2 posts this week
39 | 2027-07-05 | Phase 1 · Romania growth | Review | Phase 1 review vs goal: 100–300 users, 10–30 paying Founding Partners, 2–3 case studies
39 | 2027-07-05 | Phase 1 · Romania growth | Routine | Weekly routine + Friday numbers (see Routine and Weekly numbers)
40 | 2027-07-12 | Phase 2 · New segments | Facebook groups | Answer questions (about 2 h)
40 | 2027-07-12 | Phase 2 · New segments | Facebook Page | 2 posts this week
40 | 2027-07-12 | Phase 2 · New segments | LinkedIn | Company page + refreshed founder profile
40 | 2027-07-12 | Phase 2 · New segments | Groups | Join designer/architect groups (Facebook + LinkedIn); observe 2–3 weeks
40 | 2027-07-12 | Phase 2 · New segments | Routine | Weekly routine + Friday numbers (see Routine and Weekly numbers)
41 | 2027-07-19 | Phase 2 · New segments | Facebook groups | Answer questions (about 2 h)
41 | 2027-07-19 | Phase 2 · New segments | Facebook Page | 2 posts this week
41 | 2027-07-19 | Phase 2 · New segments | Case study | Case study #2
41 | 2027-07-19 | Phase 2 · New segments | Designers | Client-presentation angle, only if the app really shares live designs [VERIFY]
41 | 2027-07-19 | Phase 2 · New segments | Routine | Weekly routine + Friday numbers (see Routine and Weekly numbers)
42 | 2027-07-26 | Phase 2 · New segments | Facebook groups | Answer questions (about 2 h)
42 | 2027-07-26 | Phase 2 · New segments | Facebook Page | 2 posts this week
42 | 2027-07-26 | Phase 2 · New segments | Partnerships | Contact 1–2 design schools about an autumn webinar
42 | 2027-07-26 | Phase 2 · New segments | Routine | Weekly routine + Friday numbers (see Routine and Weekly numbers)
43 | 2027-08-02 | Phase 2 · New segments | Facebook groups | Answer questions (about 2 h)
43 | 2027-08-02 | Phase 2 · New segments | Facebook Page | 1 post
43 | 2027-08-02 | Phase 2 · New segments | YouTube | 1 video
43 | 2027-08-02 | Phase 2 · New segments | Prep | Webinar content + a partnership one-pager (users, case studies)
43 | 2027-08-02 | Phase 2 · New segments | Routine | Weekly routine + Friday numbers (see Routine and Weekly numbers)
44 | 2027-08-09 | Phase 2 · New segments | Facebook groups | Answer questions (about 2 h)
44 | 2027-08-09 | Phase 2 · New segments | Facebook Page | 1 post
44 | 2027-08-09 | Phase 2 · New segments | YouTube | 1 video
44 | 2027-08-09 | Phase 2 · New segments | Partnerships | Write to fittings distributors (Blum, Hettich, GTV) and CNC sellers in Romania
44 | 2027-08-09 | Phase 2 · New segments | Routine | Weekly routine + Friday numbers (see Routine and Weekly numbers)
45 | 2027-08-16 | Phase 2 · New segments | Facebook groups | Answer questions (about 2 h)
45 | 2027-08-16 | Phase 2 · New segments | Facebook Page | 1 post
45 | 2027-08-16 | Phase 2 · New segments | YouTube | 1 video
45 | 2027-08-16 | Phase 2 · New segments | Prep | Follow up on partnership replies
45 | 2027-08-16 | Phase 2 · New segments | Routine | Weekly routine + Friday numbers (see Routine and Weekly numbers)
46 | 2027-08-23 | Phase 2 · New segments | Facebook groups | Answer questions (about 2 h)
46 | 2027-08-23 | Phase 2 · New segments | Facebook Page | 1 post
46 | 2027-08-23 | Phase 2 · New segments | YouTube | 1 video
46 | 2027-08-23 | Phase 2 · New segments | Routine | Weekly routine + Friday numbers (see Routine and Weekly numbers)
47 | 2027-08-30 | Phase 2 · New segments | Facebook groups | Answer questions (about 2 h)
47 | 2027-08-30 | Phase 2 · New segments | Facebook Page | 2 posts this week
47 | 2027-08-30 | Phase 2 · New segments | LinkedIn | 5 direct conversations with manufacturers, using the case studies
47 | 2027-08-30 | Phase 2 · New segments | Routine | Weekly routine + Friday numbers (see Routine and Weekly numbers)
48 | 2027-09-06 | Phase 2 · New segments | Facebook groups | Answer questions (about 2 h)
48 | 2027-09-06 | Phase 2 · New segments | Facebook Page | 2 posts this week
48 | 2027-09-06 | Phase 2 · New segments | Webinar | Design-school webinar, or a Facebook Live demo
48 | 2027-09-06 | Phase 2 · New segments | Routine | Weekly routine + Friday numbers (see Routine and Weekly numbers)
49 | 2027-09-13 | Phase 2 · New segments | Facebook groups | Answer questions (about 2 h)
49 | 2027-09-13 | Phase 2 · New segments | Facebook Page | 2 posts this week
49 | 2027-09-13 | Phase 2 · New segments | YouTube | A video for designers
49 | 2027-09-13 | Phase 2 · New segments | Blog | A post for designers
49 | 2027-09-13 | Phase 2 · New segments | Routine | Weekly routine + Friday numbers (see Routine and Weekly numbers)
50 | 2027-09-20 | Phase 2 · New segments | Facebook groups | Answer questions (about 2 h)
50 | 2027-09-20 | Phase 2 · New segments | Facebook Page | 2 posts this week
50 | 2027-09-20 | Phase 2 · New segments | Trade show | BIFE-SIM or a regional fair if the dates fall here: tablet demos, 20–30 conversations
50 | 2027-09-20 | Phase 2 · New segments | Routine | Weekly routine + Friday numbers (see Routine and Weekly numbers)
51 | 2027-09-27 | Phase 2 · New segments | Facebook groups | Answer questions (about 2 h)
51 | 2027-09-27 | Phase 2 · New segments | Facebook Page | 2 posts this week
51 | 2027-09-27 | Phase 2 · New segments | Retention | Win-back email for cancelled users; plan Founding Partner renewal reminders (April 2028)
51 | 2027-09-27 | Phase 2 · New segments | Routine | Weekly routine + Friday numbers (see Routine and Weekly numbers)
52 | 2027-10-04 | Phase 2 · New segments | Facebook groups | Answer questions (about 2 h)
52 | 2027-10-04 | Phase 2 · New segments | Facebook Page | 2 posts this week
52 | 2027-10-04 | Phase 2 · New segments | Review | Year review: best channels for confirmed sign-ups and paying users; plan year 2
52 | 2027-10-04 | Phase 2 · New segments | Routine | Weekly routine + Friday numbers (see Routine and Weekly numbers)
Formulas:
Week starts = INDEX('Weekly plan'!$C:$C,MATCH([Week],'Weekly plan'!$A:$A,0))

## Weekly numbers
Weekly numbers
Fill in one row every Friday. Row 5 is an example of the format; the weeks start in row 6.
Week | Week starts | New confirmed sign-ups | Confirmation rate | Sign-ups via invite links | Founding Partner reservations (total) | Questions answered in groups | Facebook Page followers | YouTube subscribers | Blog + Demo page visits | blog_to_signup clicks | Notes
Example |  | 6 | 75% | 1 |  | 4 | 23 |  |  |  | Format example: replace nothing here, start in row 6
1 | 2026-10-12
2 | 2026-10-19
3 | 2026-10-26
4 | 2026-11-02
5 | 2026-11-09
6 | 2026-11-16
7 | 2026-11-23
8 | 2026-11-30
9 | 2026-12-07
10 | 2026-12-14
11 | 2026-12-21
12 | 2026-12-28
13 | 2027-01-04
14 | 2027-01-11
15 | 2027-01-18
16 | 2027-01-25
17 | 2027-02-01
18 | 2027-02-08
19 | 2027-02-15
20 | 2027-02-22
21 | 2027-03-01
22 | 2027-03-08
23 | 2027-03-15
24 | 2027-03-22
25 | 2027-03-29
26 | 2027-04-05
27 | 2027-04-12
28 | 2027-04-19
29 | 2027-04-26
30 | 2027-05-03
31 | 2027-05-10
32 | 2027-05-17
33 | 2027-05-24
34 | 2027-05-31
35 | 2027-06-07
36 | 2027-06-14
37 | 2027-06-21
38 | 2027-06-28
39 | 2027-07-05
40 | 2027-07-12
41 | 2027-07-19
42 | 2027-07-26
43 | 2027-08-02
44 | 2027-08-09
45 | 2027-08-16
46 | 2027-08-23
47 | 2027-08-30
48 | 2027-09-06
49 | 2027-09-13
50 | 2027-09-20
51 | 2027-09-27
52 | 2027-10-04
Formulas:
Week starts = INDEX('Weekly plan'!$C:$C,MATCH([Week],'Weekly plan'!$A:$A,0))
Note on C4: Where to find it: Brevo, or Plausible goal "Waitlist Confirmed"
Note on D4: Where to find it: Confirmed ÷ "Waitlist Signup" form submissions in Plausible
Note on E4: Where to find it: Plausible "Waitlist Signup" with invited = yes
Note on F4: Where to find it: Brevo Founding Partner list, or the counter on the page
Note on G4: Where to find it: Your question log
Note on H4: Where to find it: Facebook Page insights
Note on I4: Where to find it: YouTube Studio
Note on J4: Where to find it: Plausible
Note on K4: Where to find it: Plausible custom event

## Website steps
Website steps
One change in src/site.ts or src/config.ts plus a deploy each. Run npm run test:all and npm run check-launch first.
Week | Week starts | Website step | Needs first | Done
1 | 2026-10-12 | Deploy the coming-soon page | Git + GitHub, Vercel account, domain, Brevo setup (README), Plausible
13 | 2027-01-04 | home: true, privacy: true, REFERRAL_PROGRAM = true; rebuild + re-paste emails | Lawyer-approved Privacy Policy (drafts sent week 2, approved by week 12)
16 | 2027-01-25 | foundingPartner: true | BREVO_FP_LIST_ID; open questions 2–3 in DECISIONS.md decided
18 | 2027-02-08 | blog: true + first post published: true | Competitor facts verified (the [VERIFICĂ] markers)
20 | 2027-02-22 | demo: true; video IDs in src/data/demoVideos.ts | The three recorded videos
21 | 2027-03-01 | faq: true; real quotes in src/data/testimonials.ts | Answers to open questions 4–5; testers' written permission
23 | 2027-03-15 | pricing: true, terms: true | Final prices; lawyer-approved Terms
27 | 2027-04-12 | productPublic = true; Founding Partner payments live | Stripe payments built into the site (not built yet: schedule before week 23)
Formulas:
Week starts = INDEX('Weekly plan'!$C:$C,MATCH([Week],'Weekly plan'!$A:$A,0))

## Deadlines
Deadlines
If one slips, move that week's announcement, not the trust-building work around it.
Needed by week | Week starts | What | Owner | Done
1 | 2026-10-12 | Git + GitHub, Vercel, domain, Brevo setup, Plausible | Founder
12 | 2026-12-28 | Lawyer-approved Privacy Policy (blocks the referral launch) | Lawyer
14 | 2027-01-11 | Product ready for real projects (blocks the private beta) | Founder
16 | 2027-01-25 | Founding Partner open questions 2–3 decided | Founder
20 | 2027-02-22 | Demo videos recorded (weeks 18–20) | Founder
21 | 2027-03-01 | Open questions 4–5 answered (FAQ); testimonial permissions | Founder
22 | 2027-03-08 | Final prices and free-plan limits (open question 1) | Founder
23 | 2027-03-15 | Lawyer-approved Terms | Lawyer
23 | 2027-03-15 | Stripe payments built into the site | Development
Formulas:
Week starts = INDEX('Weekly plan'!$C:$C,MATCH([Needed by week],'Weekly plan'!$A:$A,0))

## Content bank
Content bank
Facebook Page posts are short: 3–6 lines plus an image or clip. Group content is mostly answers, not posts.
# | Type | Idea | From week | Used in week
1 | Trade tip | Lățimea pieselor dintre laterale: de ce se scad două grosimi | 5
2 | Trade tip | Cantul ABS de 2 mm: când și cât scazi din dimensiunea de debitare | 5
3 | Trade tip | Rosturile ușilor: 2 mm sau 3 mm? Ce iei în calcul | 5
4 | Trade tip | Balamale aplicate vs. semi-aplicate vs. interioare: diferențele de calcul | 5
5 | Trade tip | Coliziunea sertar–balama: cum o eviți înainte de tăiere | 5
6 | Trade tip | Dulapul de colț: trei soluții și dezavantajele fiecăreia | 5
7 | Trade tip | Cum îți organizezi lista de debitare ca să nu greșești la transcriere | 5
8 | Trade tip | Optimizarea plăcii: cât material pierzi de obicei și cum reduci | 5
9 | Trade tip | Ce verifici la un fișier înainte să-l trimiți la CNC | 5
10 | Trade tip | Cum măsori corect la client: lista de verificare | 5
11 | Behind the scenes | WIP screenshot: a feature a carpenter in a group asked for | 9
12 | Behind the scenes | What I learned visiting three workshops | 9
13 | Behind the scenes | Why the app runs in the browser (the founder's reason) | 9
14 | Behind the scenes | Build-log highlights from the monthly email | 10
15 | Proof | The three demo clips, each cut to 30–60 s for the Page | 21
16 | Proof | Testimonials (with permission): name, workshop, city, one concrete result | 21
17 | Proof | Case studies: one real project, before vs. after | 33
18 | Proof | "Answering your questions" videos from the question log | 28
19 | Community | The invite program: what you get for 1 and 3 confirmed invites | 13
20 | Community | Question to the audience: "Ce program folosiți acum pentru bucătării?" | 13
21 | Community | Spotlight on a beta tester's workshop (with permission) | 17
22 | Community | "You asked, we built" (Marketing Plan 6a) | 31
23 | Launch | Countdown posts: 4, 3, 2, 1 weeks | 23
24 | Launch | The founder-story post (Launch Content Kit 3.1) | 27
25 | Launch | Spots left: "X din 100 locuri Founding Partner" | 26
26 | Launch | "What we fixed in week 1" | 29

## Routine
Weekly routine
The same every week. Group presence and support are the two things never to cut.
Day | Task | Time
Monday | Facebook groups: answer new questions; update the question log | 45 min
Tuesday | Create this week's Page post or video | 1–2 h
Wednesday | Facebook groups: answers; private conversations (anchor customer, validation) | 45 min
Thursday | Publish (Facebook Page / YouTube / blog) | 30 min
Friday | Fill in "Weekly numbers"; tick off tasks; plan next week | 30 min
Every day | Reply to comments and messages within 24 hours | —
Group etiquette
• | Give value at least 9 times for every 1 mention of Mobilcab.
• | Answer the question asked, fully, even when the honest answer isn't Mobilcab.
• | Never paste the same post in every group on the same day: adapt it, and space it out.
• | Links go in a comment, not the post, if the group allows them at all.
• | If an admin says no, accept it: a ban costs a whole slice of a small market.